### How to Create a New Project Plan

You can start to manage a project by creating a new project plan in Microsoft Project. Here are the general steps you will use to create a new project plan.

Start a New Blank Project

To start a new blank project:

  - Ensure that Microsoft Project is open and displaying the Start screen.

  - On the Start screen, select Blank Project.

Start a New Project from a Template

To start a new project from a template:

  - On the Start screen, select a template.

  - In the Start Date field, type a date (or leave Today as the default).

  - Select Create.

Search for a Template

To search for a template:

  - On the Start screen, in the Search for online templates field, type a keyword or name of a template.

  - Select the Start searching button.

Capturing the appropriate information will help you find and remember important details about your project. Here are the general steps you will use to define the information for a project.

Change the Project Scheduling Mode

To change the project scheduling mode:

  - From the Project tab, open the Project Information dialog box.

  - In the Schedule from drop-down list, select a scheduling mode (Project Start Date or Project Finish Date).

Change the Start Date

To change the project start date:

  - From the Project tab, open the Project Information dialog box.

  - In the Start date box, select a new date.

Change the Finish Date

To change the project finish date if you have scheduled from the finish date:

  - From the Project tab, open the Project Information dialog box.

  - In the Finish date box, select a new date.

Change the Current Date

To change the date that Microsoft Project uses as the current date:

  - From the Project tab, open the Project Information dialog box.

  - In the Current date box, select a new date.

Save a Project File to Your Computer

To save a Microsoft Project file to your computer:

  - On the File tab, select Save As.

  - Browse to a location to save the file, and name the file.

In many projects, you need to specify the working times and non-working times using project calendars. Here are the general steps you will use to work with project calendars.

Copy a Base Calendar

To create a new base calendar from an existing calendar:

  - From the Project tab, select Change Working Time.

  - Select Create New Calendar, and name it. Make sure that the Make a copy of radio button is selected, and select a base calendar to copy from.

Add an Exception

To add a working time exception:

  - From the Project tab, select Change Working Time.

  - Select a date or dates on the calendar.

  - In the Exceptions table, select the highlighted cell and enter a name for the exception.

Set the Working Time of an Exception

To set the working time of an exception:

  - From the Project tab, select Change Working Time.

  - In the Exceptions table, select an exception, then the Details button to the right.

  - Below the Working times radio button, modify a From or To time, select the cell and enter the new time. To delete a row of From and To times, select the row and press Delete.

Set a Recurrence Pattern

To set a recurrence pattern for an exception:

  - From the Project tab, select Change Working Time.

  - In the Exceptions table, select an exception, then the Details button to the right.

  - Select the Daily, Weekly, Monthly, or Yearly radio button as appropriate.

  - Select the appropriate recurrence pattern and range of occurrence.

Assign a Calendar to the Project

To assign a calendar:

  - From the Project tab, open the Project Information dialog box.

  - In the Calendar drop-down list, select a base calendar (24 Hours, Night Shift, Standard, or a calendar that you created).

The key pieces of information you need to complete your project plan are tasks. Here are the general steps you will use to add tasks to a project; define relationships between tasks; change how a task is scheduled; and set task constraints and deadlines. When you have completed these tasks, you will have a project schedule.

Add a New Task

To add a new task:

- Make sure you are in Gantt Chart view.

- In the Task Entry table, find the cell in the first empty row of the Task Name column, and type the name of the task in that cell.

Set a Task's Duration

To set the duration of task:

- Make sure you are in Gantt Chart view.

- In the Task Entry table, find the Duration column for the task you wish to modify, and enter the number and unit, for example 1 day or 2 weeks.

- To make the Duration an estimate, add a question mark, for example 1 day?

Link Tasks

To link tasks:

- Make sure you are in Gantt Chart view.

- In the Task Entry table, highlight the tasks you wish to link.

- On the ribbon, in the Schedule group of the Task tab, select the Link the Selected Tasks button.

Define Task Relationships

To change the relationship type between a task and its predecessor:

- Double-click the successor task in the Task Entry table.

- In the Predecessors tab of the Task Information dialog box, select the predecessor task relationship you want to change and select the appropriate relationship type.

Add Lag Time

To add lag time to linked tasks:

- Double-click the successor task in the Task Entry table.

- In the Predecessors tab of the Task Information dialog box, enter a positive value and the unit of time in the Lag column, for example, 1 day to set a lag of one day.

Add Lead Time

To add lead time to linked tasks:

- Double-click the successor task in the Task Entry table.

- In the Predecessors tab of the Task Information dialog box, enter a negative value and the unit of time in the Lag column, for example, -1 day to set a lead time of one day.

Set a Constraint on a Task

To set a constraint on a task:

- Double-click the task to open the Task Information dialog box.

- In the Advanced tab, select the desired constraint type, and in the Constraint date box, enter or select a date for the constraint.

Set a Deadline for a Task

To set a deadline for a task:

- Double-click the task to open the Task Information dialog box.

- In the Advanced tab, enter or select a date for the deadline.